## Лист1
PROGRESS REPORT
ID | Test name | Responsibility | Resourses | Deadline | Satus | Date completed | Comments
1 | Main algorithm | ABPozharliev19 | Visual studio code | 24.10.2021 | completed | 23.10.2021
2 | Game Main Menu | BNSavov19 KSChervenkov19 | Visual studio code | 24.10.2021 | completed | 20.10.2021
3 | Team Logo | BNSavov19 | Photoshop | 9.11.2021 | completed | 22.10.2021
4 | Character movement | BNSavov19 KSChervenkov19 | Visual studio code | 9.11.2021 | completed | 20.10.2021
5 | Lobby and rooms | BNSavov19 KSChervenkov19 | Visual studio code | 9.11.2021 | completed | 19.10.2021
6 | Main menu background | BNSavov19 | Photoshop | 9.11.2022 | open
7 | Other game mechanics | ABPozharliev19 BNSavov19 KSChervenkov19 | Visual studio code | 9.11.2023 | in progress