## Лист1
PROGRESS REPORT
ID | Test name | Responsibility | Resourses | Deadline | Satus | Date completed | Comments
1 | Main algorithm | ABPozharliev19 | Visual studio code | 24.10.2021 | completed | 23.10.2021
2 | Game Main Menu | BNSavov19 KSChervenkov19 | Visual studio code | 24.10.2021 | completed | 20.10.2021
3 | Team Logo | BNSavov19 | Photoshop | 9.11.2021 | completed | 22.10.2021
4 | Character movement | BNSavov19 KSChervenkov19 | Visual studio code | 9.11.2021 | completed | 20.10.2021
5 | Lobby and rooms | BNSavov19 KSChervenkov19 | Visual studio code | 9.11.2021 | completed | 19.10.2021
6 | Main menu background | BNSavov19 | Photoshop | 9.11.2021 | completed | 8.11.2021
7 | Add scrolls and runes | BNSavov19 KSChervenkov19 | Visual studio code | 9.11.2021 | completed | 5.11.2021
8 | Character design | BNSavov19 KSChervenkov19 | Visual studio code | 9.11.2021 | completed | 3.11.2021
9 | Collisions | ABPozharliev19 BNSavov19 KSChervenkov19 | Visual studio code | 9.11.2021 | completed | 5.11.2021
10 | Git Hub work | ABPozharliev19 |  | 9.11.2021 | completed | 8.11.2021
11 | QA documentation | IGVasilev19 | Microsoft Excel Microsoft Word | 9.11.2021 | completed | 8.11.2021
12 | Finish Game and Project documentation | ABPozharliev19 BNSavov19 KSChervenkov19 IGVasilev19 | Microsoft Excel Microsoft Word Visual studio code Visual Studio 2019 Microsoft PowerPoint | 9.11.2021 | completed | 8.11.2021